## REQ
Review point | section | Reviewer | Status | Author Comments
To increase accuracy sensor can be changed | Requirements diagram 4.1 | Namık Mert Tunçbilek | closed | Vignesh: Accepted Changed RADAR to LiDAR 4.1 to 4.2 Closed
To increase accuracy sensor can be changed | Requirements diagram 16.1 | Namık Mert Tunçbilek | closed | Vignesh: Accepted Changed RADAR to LiDAR 16.1 to 16.2 Closed

## UseCaseD
Review point | section | Reviewer | Status | Author Comments
The Package name is mismatching with the naming convention | All Use case diagram | Vignesh Arumugam | closed | Namik Mert Tunçbilek: Accepted - Package names were changed
Do we need two actors? | Data sharing in platoon | Vignesh Arumugam | closed | Namik Mert Tunçbilek: Accepted - Actor2(Trucks in Platoon was removed)

## ActivityD
Review point | section | Reviewer | Status | Author Comments
Conditions should be specified | Activity Diagram | Veli | closed | Mirudhubashini Ramasamy Sridharan: Accepted and conditons are updatetd
Received Data should be transferred to the following trucks, not leading truck | Activity Diagram | Veli | closed | Mirudhubashini Ramasamy Sridharan: Accepted and flow changes were updatetd

## BlockDefinitionD
Review point | section | Reviewer | Status | Author Comments
"Follow" block diagram is not correct as per standard | Camera block diagram | Veli | closed | Updated

## SequenceD
Review point | section | Reviewer | Status | Author Comments
Sequence diagram is not syncing with the input diagram, the block diagram | All | Vignesh | closed | Nijat Dashdamirov: Accepted and Updated

## AllocationD
Review point | section | Reviewer | Status | Author Comments
Why sensors is shown in different blocks? | Sensor block | Nijat Dashdamirov | closed | Namik Mert Tuncbilek: Accepted - Sensor blocks are merged

## InternalBlockD
Review point | section | Reviewer | Status | Author Comments
Usage of multiple cameras will bring out accurate outputs | Internal Block Diagram | Mirudhu | closed | Namik Mert Tuncbilek: Accepted - Number of used cameras was increased

## ParametricConstraintsD
Review point | section | Reviewer | Status | Author Comments
Why parametric constraints blocks not used? | All | Namik Mert Tuncbilek | closed | Vignesh: The purpose of parameteric constraint block is used, when we have a general constraint block which can be assigned or used by another block. Here in this block diagram we can able to handle the constraint diagram wihtout the constraint block

## StateMachineD
Review point | section | Reviewer | Status | Author Comments
Received and transfering signals should be merged as communication state | Sensor component | Vignesh | closed | Veli: Accepted and Updated
Initialising of communication should be added at the begining of the diagram | Sensor component | Mirudhu | closed | Veli: Accepted and Updated

## CodeImp
Review point | section | Reviewer | Status | Author Comments
Task priority is not syncing with scheduling. | All | Namik Mert Tuncbilek | closed | accepted and updated

## Scheduling
Review point | section | Reviewer | Status | Author Comments
Why RMS not performed? |  | Namik Mert Tuncbilek | closed | Some tasks are need to be finished earlier and those had the less computation. So EDF has been prefered than the RMS

## UnitT
Review point | section | Reviewer | Status | Author Comments
Each test cases can be performed individually for each functions | All | Vignesh | closed | Namik Mert Tuncbilek: Accepted - Test cases were separated for each functions

## ComponentT
Review point | section | Reviewer | Status | Author Comments
Why component testing is done in the main SRC folder | All | Vignesh | closed | Nijat Dashdamirov:Because in our case only main.cpp file is running I put all the functions inside of the main.cpp